## Guide
DBIZ2 · Session 7 — Workshop workbook
PURPOSE | One sheet per workshop block (W0–W5). Each sheet's output is the next sheet's input, wired with real formulas. Nothing is retyped between sheets.
ADD / REMOVE | Every table has spare rows and every formula spans the whole table, so adding or deleting a function anywhere updates the rest of the workbook automatically. Type into the next blank row; clear a row to delete it. Do not delete whole spreadsheet rows.
IF A FORMULA BREAKS | Never type into a green or black cell. If you do, clear it and copy the formula down from the row above. The integrity line at the bottom of W1 reports any row that lost its Base hours formula.
SEED DATA | A small worked example ships with the workbook — LabDesk, a computer-lab reservation system, with three features. Teams clear it and enter their own project.
Data chain
Sheet | Block | Input taken from | Output flowing out | Cells the team fills | Owner
Parameters | before the session | Rates, factors, capacity, thresholds set by the lecturer | Every derived number in W1, W2, W4, W5 | All yellow cells | Lecturer
W0_Scope | W0 | Use Case Diagram; CVCA; Context Diagram | Feature list → W1; data functions → FP count; Won't-have → W5 | Tables 1–4 | Whole team
W1_FunctionList | W1 | Features from W0; the five design diagrams | L2 and L3 rows → W2_Costing and W4 | Columns A–J, L–N | Feature owners
W2_Costing | W2 | W1 rows; Parameters | Cost per L3 and per L2; function-point cross-check → W2_Rollup | Nothing — fully derived | —
W2_Rollup | W2 | W2_Costing | Machine signals → W3; three headline figures → W5 | Three shared observations | Integrator
W3_CrossReview | W3 | Machine signals from W2_Rollup | Defect log → W4 buckets | Blue = owning team · Orange = reviewing team | Two teams
W4_Prioritization | W4 | Initial priority from W1; defects from W3 | Effective priority → back into W2_Costing | Rule, Kano, new priority, justification | Whole team
W5_Handover | W5 | Three figures from W2_Rollup; Parameters | business-case.md, tasks.md, Session 8 | Open questions and notes | Integrator
Colour convention
Blue text | A cell you type into
Black text | A formula computed inside this sheet — do not overwrite
Green text | A formula pulling from another sheet — do not overwrite
Yellow fill | A cell that must be filled in
Light blue fill | Filled by the OWNING team (W3 only)
Orange fill | Filled by the REVIEWING team (W3 only)
Three rules said out loud
1. One diagram per sweep. Mixing diagrams destroys the source trail — for people and for AI alike.
2. Cut by lowering priority, never by lowering effort.
3. Green cells and the whole W2 block are derived views. If a number looks wrong, fix the source and recalculate.

## Parameters
Parameters — Fixed for the whole class
INPUT | Labour-market data, productivity assumptions and the team capacity, fixed for the whole cohort.
OUTPUT | Every derived number in W1, W2, W4 and W5 traces back to a cell on this sheet.
WHY FIXED | If each team invented its own rates the exercise would test guessing rather than the model, and results would not be comparable at marking. The point of a published parameter is that the subjectivity sits in ONE auditable place instead of forty scattered ones.
1. Effort size to base hours (applied at level 3)
Size | Hours |  | Note
S | 4 |  | Ceiling for one L3 row is 16 h — above that it is not yet an L3 row
M | 8 |  | Matches the test: ask a developer; an answer of 4–16 h is correct granularity
L | 16
2. Technical layer to AI leverage and default seniority
Layer | AI leverage factor | Default band | Note
FE | 0.35 | Junior | Screens, forms, repeated patterns — AI generates these well
BE | 0.7 | Senior | Business logic, state, concurrency
INT | 1 | Senior | Third-party APIs, credentials, sandboxes — AI helps least here
3. Hourly cost by seniority band (VND / hour)
Band | Rate |  | Source
Junior | 200000 |  | ITviec 2025-26 median 25.35m VND/month x 1.35 overhead / 176 h
Senior | 300000 |  | ITviec 2025-26 median 39.9m VND/month x 1.35 / 176 h
Expert | 400000 |  | ITviec 2025-26 median 54.9m VND/month x 1.35 / 176 h
4. Verification factor (driven by acceptance-criterion quality)
EARS precise? | Factor |  | Note
Yes | 0.15 |  | Clear criteria — fast to verify, often automatable
No | 0.4 |  | Vague criteria — a person must reason the answer out from scratch
5. Function point weights (IFPUG average complexity)
FP type | Weight |  | What it counts
EI | 4 |  | External Input — data crosses the boundary inward and changes stored data
EO | 5 |  | External Output — data leaves the boundary WITH derived values or calculation
EQ | 4 |  | External inQuiry — retrieval only, no derived data, nothing stored changes
ILF | 10 |  | Internal Logical File — a group of data the system itself maintains
EIF | 7 |  | External Interface File — data the system reads but never maintains
NC | 0 |  | Not countable — a business rule or non-functional item inside another transaction
Hours per unadjusted function point | 3 |  | Class parameter, PRE-AI gross hours. Published industry figures range very widely; calibrate this from your own delivered projects rather than importing a benchmark
6. Team capacity for DBIZ3
Team members | 6
Weeks | 12
Productive hours per person per week | 5 |  | Hours actually spent building, not hours present
Total capacity (person-hours) | 360 |  | Hard ceiling for the whole scope: Must + Should + Could
7. Thresholds
Must, maximum share of scope effort | 60% |  | DSDM: above 60% the project enters the risk zone
Could, target share of scope effort | 20% |  | The contingency pool, expressed as scope rather than money
Hidden technical work, minimum share | 10% |  | Real projects run 20–30%; below 10% something is missing
Maximum hours for one L3 row | 16
Minimum number of features | 3
Maximum number of features | 6
Estimate variance that triggers a review | 30% |  | If bottom-up and function-point estimates differ by more than this, something is mis-sized
8. Formulas
Person-hours = base hours x AI leverage factor + base hours x verification factor
Cost = person-hours x hourly rate for the seniority band
Function-point cross-check = unadjusted function points x hours per FP (compare against total base hours)
Note: once a ~20% Could pool exists as scope contingency, do NOT add a further 20% money contingency on top — that counts the same buffer twice.
9. Estimation basis — which method drives the hours
Estimation basis | Bottom-up |  | Switch this and the whole workbook recalculates on the other method.
Bottom-up: base hours come from the S / M / L label on each L3 row. Function-point: the L2 total comes from its function-point count x hours per FP, then S / M / L acts only as the RELATIVE weight that distributes those hours across the L3 rows. NC rows have no function points, so they always fall back to bottom-up — that is the 0 function point problem, and it is why the two methods can never fully replace each other.

## W0_Scope
W0 — Establish scope and split into features
INPUT | The Use Case Diagram, the CVCA and the Context Diagram, updated after the user meeting. Every diagram element must already carry an ID.
OUTPUT | (a) a complete use-case inventory, (b) a small set of features, each a folder under specs/, (c) an explicit Won't-have list, (d) the data functions the system maintains or reads. Feature IDs feed column A of W1.
PROCEDURE | 1. List EVERY use case in Table 1 — names only, no discussion yet. 2. Cluster them into features in Table 2. A feature name is a business noun the client recognises, never a screen name or a technical module. 3. Coverage check against the CVCA: every primary actor must be served by at least one feature. 4. Record anything excluded in Table 3, with the reason. 5. In Table 4, list the data the system MAINTAINS (ILF) and the data it only READS from another system (EIF). Read these off the Context Diagram boundary.
RULE | Merge any feature expected to hold fewer than 3 L2 rows. A feature that no use case and no CVCA flow points at does not belong in the release.
Table 1 · Use case inventory — list every use case before clustering
Use case ID | Use case name | Primary actor | Assigned feature | Login required
UC-01 | View book shelf location | Reader | F-01 | No
UC-02 | Browse interactive digital library map | Reader | F-01 | No
UC-03 | Filter books by access format (online, physical or both) | Reader | F-03 | No
UC-04 | Write, edit and delete own book reviews | Reader | F-02 | Yes
UC-05 | View book reviews | Reader | F-02 | No
UC-06 | Access book information and reviews via QR code (physical books; reviews via UC-04) | Reader | F-02 | No
UC-07 | Update and view personal reading history and preferences | Reader | F-03 | Yes
UC-08 | AI-based conversational book search | Reader | F-03 | Yes
UC-09 | Automatic personalised book recommendations | Reader | F-03 | Yes
UC-10 | Print QR code labels for physical books (QR codes are generated automatically) | On-site Staff | F-02 | Staff login
UC-11 | Register and sign in (library card with email OTP) | Reader | F-04 | No
UC-12 | Save physical books to a personal list for finding them later in the library, and remove them from the list | Reader | F-03 | Yes
UC-13 | Remove reviews that violate rules | On-site Staff | F-02 | Staff login
UC-14 | Report a review that violates rules | Reader | F-02 | Yes
Table 2 · Feature list — this is what flows into W1
Feature ID | Feature name (business noun) | Scope in one sentence | Primary actors served | Owner | Use cases covered
F-01 | Book Location & Library Map | Readers see the exact shelf location of each book and browse a digital map of floors and reading rooms. | Reader | Owner A | UC-01, UC-02
F-02 | Reviews & QR | Readers write, edit, delete and read reviews of books, including by scanning a QR code on a physical book, and On-site Staff print the QR labels and remove reviews that violate rules. | Reader, On-site Staff | Owner C | UC-04, UC-05, UC-06, UC-10, UC-13, UC-14
F-03 | Discovery, Reading History & Recommendation | Readers filter books by access format (online, physical or both), keep a reading history and a saved-books list, and get AI chatbot search and recommendations based on their preferences. | Reader | Owner D | UC-03, UC-07, UC-08, UC-09, UC-12
F-04 | Platform, Access & Operations | Readers sign in (library card with email OTP), On-site Staff sign in with their internal library accounts to reach their minimal page, and the platform syncs data from the library's internal system, is deployed and keeps an audit log. | All actors | Owner A | UC-11
Feature count | 4 | PASS
Table 3 · Won't-have — record it here, never drop it silently
Excluded from scope | How it surfaced | Reason for exclusion
Automatic tracking of reading progress and finished books | Stated in the note under UC-07 | The library records borrow/return of physical books but not pages read. Online books opened by library card readers and borrowed physical books enter the history automatically; readers mark Reading or Finished and enter progress manually in release 1
Borrowing, returning and renewing loans | Implied by former UC-05 ('ready for borrowing', removed from the diagram); no loan use case in the diagram | Stays in the library's internal system; this platform does not handle loans. The current OPAC already shows copy availability and the Borrow action
Reading online content inside the platform | Implied by UC-03 (Online format); no viewer use case in the diagram | Confirmed: online books can be opened or downloaded without sign-in on the existing OPAC; this platform builds no viewer and no download of its own
Assigning or editing shelf codes and the library layout | Implied by the original UC-01 (Manage book locations) | Done in the library's internal system; this platform only reads the data and publishes it to readers
Full librarian/admin workspace in the OPAC | Implied by the original actor Librarian/Admin | Staff use only a minimal page (QR label printing, review removal) with their internal accounts; catalogue, shelf codes and loans are managed in the internal system
Traditional keyword search | Not in any use case | Already provided by the current OPAC; this platform adds filtering and AI chatbot search only
QR codes for online-only books | Business rule on UC-06 | Online-only books have no physical copy to attach a QR code to; readers download the PDF instead
Sending reader reviews and feedback to the library's internal system, or a report/dashboard of them for library staff | Implied by the CVCA flow 'reader feedback & rate books' to the library (flow to be removed from the CVCA) | Reviews and feedback stay in this platform and are not sent to the internal system
Screen for library staff to edit floor plans and rooms | Implied by UC-02 (digital library map) | No digital floor plan exists today; the team prepares it once. Changes to the room layout are made by the team, not through a screen in release 1
Features not rebuilt: (a) like/dislike rating, list of books in a room, copy availability and borrow status, already on the current OPAC; (b) viewing and filtering by collection status (In collection / Coming soon) | (a) Confirmed on the current OPAC (document location panel shows each copy, its circulation point and status); (b) former UC-03, dropped after team review | (a) Not rebuilt. This platform keeps text reviews only and does not read copy circulation status. (b) The internal system holds the field, but readers do not need it on the web
Showing the access format of each book on the book detail page (FR-03-14) and downloading PDFs on this platform (FR-03-15) | Scope cut after the W4 capacity review (UC-03 reduced to the access-format filter) | Download PDF: the current OPAC already has this function and online books can be downloaded without sign-in, so it is not rebuilt. Access format display: for physical books the OPAC already shows the number of copies and the shelf location; for online books it already shows a download button. This platform only adds the online / physical / both filter (FR-03-12)
Online reader accounts: register or sign in with email OTP (FR-04-02), Google sign-in (FR-04-03), linking an online account to a library card and its check (FR-04-05, FR-04-06) | Scope cut after the W4 capacity review (UC-11 online part) | Only library card holders sign in (library card + email OTP, FR-04-01). Online books are opened or downloaded without any account, so there is nothing to link
Error tracking, health check and alerts to the project team (FR-04-15) | Hidden work in F-04, cut after the W4 capacity review | Deferred to fit team capacity; the team checks the system by hand in release 1
Table 4 · Data functions — what the system maintains (ILF) or only reads (EIF)
Data group | ILF / EIF | Why | Function points
Book placement & library layout | EIF | Rooms, shelf codes and book-to-shelf assignments, plus the list of floors and rooms, read from the library's internal system, never written (UC-01, UC-02). The floor-plan drawing is a fixed asset built once by the project team, not a data function; its room codes must match the internal system | 7
Book review | ILF | Written by readers, stored and shown by the system; readers can report a review and staff can remove reviews that violate rules (UC-04 to UC-06, UC-13, UC-14) | 10
Reading history & preferences | ILF | History entries are added automatically (opening of an online book by a library card reader; borrow of a physical book, library card accounts only); status Reading/Finished, progress and preferences are entered by readers (UC-07, UC-09) | 10
Book catalogue | EIF | Titles, authors, subjects, summaries and access formats read from the library's internal system, never written (UC-03, UC-06) | 7
Reader accounts | EIF | Reader identity, library card number and the email declared when the card was made (used to send the OTP) read from the library's existing reader accounts, never written (UC-11) | 7
Book QR codes | ILF | QR codes generated automatically for each new physical book, with scan counts kept for analysis and AI training; also the entry point for writing reviews (UC-06, UC-10) | 10
Saved books list | ILF | Physical books that readers save, with a library card account, to find them later in the library (UC-12) | 10
Reader loan records | EIF | Borrow/return history of each library card account, read from the library's internal system, never written (UC-07) | 7
Chatbot conversations | ILF | Messages and needs readers state to the chatbot, saved per reader to personalise search and recommendations (UC-08, UC-09) | 10
Staff accounts | EIF | On-site Staff identity read from the library's internal accounts, never written (sign-in to the staff page) | 7
Online book read log | ILF | Book ID and time of each online-book read, stored without any reader identity, kept to analyse use and to train the AI features (UC-03) | 10
|  | Total data-function points | 95

## W1_FunctionList
W1 — Decompose features into the function list
INPUT | The feature list from W0 and the five design diagrams: Use Case, Sequence, Context (DFD L0), CVCA, Architecture + ADR.
OUTPUT | Every function at two levels. L2 = a business behaviour the client signs off, carrying the EARS criterion and the function-point type. L3 = one work item in one technical layer. No money on this sheet.
PROCEDURE | 1. Sweep the five diagrams, ONE DIAGRAM PER PASS. Record every candidate with the diagram element it came from. 2. Merge duplicates — keep one row, accumulate the sources in column E. 3. Write one EARS sentence per L2 row. 4. Classify each L2 row by function-point type: EI, EO, EQ, or NC when it is a rule or a non-functional item living inside another transaction. 5. Split each L2 into L3 rows by layer (FE / BE / INT) and give each a size. 6. Set an initial MoSCoW priority by instinct. W4 is where it is tightened.
WATCH FOR | Many valuable rows are NC — 'prevent double booking', 'enforce authorisation', 'deploy automatically'. They score zero function points and are often the most expensive rows in the sheet. That gap is the reason the function-point count is a CROSS-CHECK, never the estimate itself.
ADD / REMOVE | Type into the next blank row to add a function; clear a row's contents to remove it. Every other sheet follows automatically.
Feature | L2 ID | L2 function name | Actor | EARS acceptance criterion | Source trace | Dependency | Initial priority | FP type | L3 ID | Layer | L3 work item | Size | Base hours | EARS precise? | Hidden work? | New L2 | L2 index | FP value
F-01 | FR-01-01 | View book shelf location | System | WHEN a reader opens a book detail page, the system SHALL display the floor, room and shelf code where the book is placed. | UC:UC-01; DFD L0: Book placement & library layout (EIF) | – | Must | EQ | FR-01-01-FE | FE | Screen: shelf location panel on the book detail page | S | 4 | Yes | No | 1 | 1 | 4
F-01 | FR-01-01 | View book shelf location | System | WHEN a reader opens a book detail page, the system SHALL display the floor, room and shelf code where the book is placed. | UC:UC-01; DFD L0: Book placement & library layout (EIF) | FR-01-01 | Must | EQ | FR-01-01-BE | BE | API: get floor, room and shelf code by book ID | S | 4 | Yes | No | 0 | 1 | 0
F-01 | FR-01-02 | Browse the digital library map | System | WHEN a reader opens the library map, the system SHALL display the floors and the reading rooms of each floor. | UC:UC-02; DFD L0: Book placement & library layout (EIF) | FR-01-01 | Must | EQ | FR-01-02-FE | FE | Screen: interactive floor plan with floor switcher and clickable rooms | L | 16 | Yes | No | 1 | 2 | 4
F-01 | FR-01-02 | Browse the digital library map | System | WHEN a reader opens the library map, the system SHALL display the floors and the reading rooms of each floor. | UC:UC-02; DFD L0: Book placement & library layout (EIF) | FR-01-02 | Must | EQ | FR-01-02-BE | BE | API: list floors and rooms | S | 4 | Yes | No | 0 | 2 | 0
F-01 | FR-01-03 | Show a book's room on the map | System | WHEN a reader selects the map link on a book shelf location, the system SHALL open the library map with the room that holds the book highlighted. | UC:UC-01; UC:UC-02 | FR-01-02 | Should | EQ | FR-01-03-FE | FE | Screen: map view with highlighted room and deep link from book detail | M | 8 | Yes | No | 1 | 3 | 4
F-01 | FR-01-03 | Show a book's room on the map | System | WHEN a reader selects the map link on a book shelf location, the system SHALL open the library map with the room that holds the book highlighted. | UC:UC-01; UC:UC-02 | FR-01-03 | Should | EQ | FR-01-03-BE | BE | API: return room map coordinates with the shelf location | S | 4 | Yes | No | 0 | 3 | 0
F-01 | FR-01-04 | Prepare the digital floor plan | System | The system SHALL provide a digital floor plan of every floor in which each reading room carries the same room code as the internal library system. | W0 Table 4 note (floor plan is a fixed asset built once by the project team) | FR-01-03 | Must | NC | FR-01-04-FE | FE | Asset: draw the digital floor plan of each floor and tag every room with its room code | L | 16 | Yes | Yes | 1 | 4 | 0
F-01 | FR-01-05 | Check room codes against the internal system | System | WHEN a sync run finishes, the system SHALL report every room code on the floor plan that has no matching room code in the synced layout, and every synced room code that has no room on the floor plan. | Derived: W0 Table 4 note (floor plan room codes must match the internal system) | FR-01-04 | Should | NC | FR-01-05-BE | BE | Job: compare synced room codes with floor plan room codes and report mismatches | M | 8 | Yes | Yes | 1 | 5 | 0
F-02 | FR-02-01 | Write a book review | System | WHEN a signed-in reader submits a review text for a book, the system SHALL save it against that book and that reader. | UC:UC-04; DFD L0: Book review (ILF) | – | Must | EI | FR-02-01-FE | FE | Screen: review form | S | 4 | Yes | No | 1 | 6 | 4
F-02 | FR-02-01 | Write a book review | System | WHEN a signed-in reader submits a review text for a book, the system SHALL save it against that book and that reader. | UC:UC-04; DFD L0: Book review (ILF) | FR-02-01 | Must | EI | FR-02-01-BE | BE | API: validate and save review | S | 4 | Yes | No | 0 | 6 | 0
F-02 | FR-02-02 | View book reviews | System | WHEN a reader opens the reviews of a book, the system SHALL display the list of reviews for that book. | UC:UC-05; DFD L0: Book review (ILF) | FR-02-01 | Must | EQ | FR-02-02-FE | FE | Screen: paged review list | M | 8 | Yes | No | 1 | 7 | 4
F-02 | FR-02-02 | View book reviews | System | WHEN a reader opens the reviews of a book, the system SHALL display the list of reviews for that book. | UC:UC-05; DFD L0: Book review (ILF) | FR-02-02 | Must | EQ | FR-02-02-BE | BE | API: list reviews with pagination | S | 4 | Yes | No | 0 | 7 | 0
F-02 | FR-02-03 | Edit own review | System | WHEN a signed-in reader submits an edited text for their own review, the system SHALL replace the review text and keep the review linked to the same book. | UC:UC-04 (extension: edit own review, team decision); DFD L0: Book review (ILF) | FR-02-02 | Could | EI | FR-02-03-FE | FE | Screen: edit action on own review | S | 4 | Yes | No | 1 | 8 | 4
F-02 | FR-02-03 | Edit own review | System | WHEN a signed-in reader submits an edited text for their own review, the system SHALL replace the review text and keep the review linked to the same book. | UC:UC-04 (extension: edit own review, team decision); DFD L0: Book review (ILF) | FR-02-03 | Could | EI | FR-02-03-BE | BE | API: update own review | S | 4 | Yes | No | 0 | 8 | 0
F-02 | FR-02-04 | Delete own review | System | WHEN a signed-in reader confirms the deletion of their own review, the system SHALL remove that review from public display. | UC:UC-04 (extension: delete own review, team decision); DFD L0: Book review (ILF) | FR-02-03 | Could | EI | FR-02-04-FE | FE | Screen: delete action with confirmation on own review | S | 4 | Yes | No | 1 | 9 | 4
F-02 | FR-02-04 | Delete own review | System | WHEN a signed-in reader confirms the deletion of their own review, the system SHALL remove that review from public display. | UC:UC-04 (extension: delete own review, team decision); DFD L0: Book review (ILF) | FR-02-04 | Could | EI | FR-02-04-BE | BE | API: remove own review from public display | S | 4 | Yes | No | 0 | 9 | 0
F-02 | FR-02-05 | Open book information and reviews via QR code | System | WHEN a reader scans the QR code on a physical book, the system SHALL open the information and review page of that book. | UC:UC-06; DFD L0: Book QR codes (ILF) | FR-02-04 | Must | EQ | FR-02-05-FE | FE | Screen: mobile landing page for a scanned QR code | S | 4 | Yes | No | 1 | 10 | 4
F-02 | FR-02-05 | Open book information and reviews via QR code | System | WHEN a reader scans the QR code on a physical book, the system SHALL open the information and review page of that book. | UC:UC-06; DFD L0: Book QR codes (ILF) | FR-02-05 | Must | EQ | FR-02-05-BE | BE | API: resolve QR code to book | S | 4 | Yes | No | 0 | 10 | 0
F-02 | FR-02-06 | Count QR code scans | System | WHEN a QR code is scanned, the system SHALL increase the scan count of that QR code by one. | UC:UC-06; DFD L0: Book QR codes (ILF), scan counts | FR-02-05 | Should | NC | FR-02-06-BE | BE | Increase the scan counter on each QR code resolve | S | 4 | Yes | No | 1 | 11 | 0
F-02 | FR-02-07 | Generate QR codes for new physical books | System | WHEN a new physical book appears in the synced catalogue, the system SHALL generate a unique QR code linked to that book. | UC:UC-10; DFD L0: Book QR codes (ILF); W0 Table 3 (no QR code for online-only books) | FR-02-06 | Must | NC | FR-02-07-BE | BE | Job: generate and store a unique QR code for each new physical book | M | 8 | Yes | No | 1 | 12 | 0
F-02 | FR-02-08 | Print QR code labels | System | WHEN signed-in On-site Staff select books and choose Print labels, the system SHALL produce a printable sheet of QR code labels for the selected books. | UC:UC-10 | FR-02-07 | Must | EQ | FR-02-08-FE | FE | Screen: staff page to select books and preview the label sheet | M | 8 | Yes | No | 1 | 13 | 4
F-02 | FR-02-08 | Print QR code labels | System | WHEN signed-in On-site Staff select books and choose Print labels, the system SHALL produce a printable sheet of QR code labels for the selected books. | UC:UC-10 | FR-02-08 | Must | EQ | FR-02-08-BE | BE | API: build the printable label sheet (PDF) | M | 8 | Yes | No | 0 | 13 | 0
F-02 | FR-02-09 | Report a review that breaks the rules | System | WHEN a signed-in reader reports a review, the system SHALL save the report against that review. | UC:UC-14 | FR-02-08 | Could | EI | FR-02-09-FE | FE | Screen: Report action on a review | S | 4 | Yes | No | 1 | 14 | 4
F-02 | FR-02-09 | Report a review that breaks the rules | System | WHEN a signed-in reader reports a review, the system SHALL save the report against that review. | UC:UC-14 | FR-02-09 | Could | EI | FR-02-09-BE | BE | API: save a report against a review | S | 4 | Yes | No | 0 | 14 | 0
F-02 | FR-02-10 | Review and remove reported reviews | System | WHEN signed-in On-site Staff confirm the removal of a review from the reported reviews list, the system SHALL remove that review from public display. | UC:UC-13; UC:UC-14 | FR-02-09 | Could | EI | FR-02-10-FE | FE | Screen: staff list of reported reviews with Remove action and confirmation | M | 8 | Yes | No | 1 | 15 | 4
F-02 | FR-02-10 | Review and remove reported reviews | System | WHEN signed-in On-site Staff confirm the removal of a review from the reported reviews list, the system SHALL remove that review from public display. | UC:UC-13; UC:UC-14 | FR-02-10 | Could | EI | FR-02-10-BE | BE | API: list reported reviews and remove a review from public display | M | 8 | Yes | No | 0 | 15 | 0
F-03 | FR-03-01 | View reading history | System | WHEN a signed-in reader opens the reading history page, the system SHALL display the history entries of that reader with their reading status. | UC:UC-07; DFD L0: Reading history & preferences (ILF) | – | Should | EQ | FR-03-01-FE | FE | Screen: reading history list with status | M | 8 | Yes | No | 1 | 16 | 4
F-03 | FR-03-01 | View reading history | System | WHEN a signed-in reader opens the reading history page, the system SHALL display the history entries of that reader with their reading status. | UC:UC-07; DFD L0: Reading history & preferences (ILF) | FR-03-01 | Should | EQ | FR-03-01-BE | BE | API: list history entries of the signed-in reader | S | 4 | Yes | No | 0 | 16 | 0
F-03 | FR-03-02 | Add a history entry when an online book is opened or downloaded | System | WHEN a signed-in library card reader opens or downloads an online book from this platform, the system SHALL add that book to the reading history of that reader. | UC:UC-07; UC:UC-03 | FR-03-01 | Should | NC | FR-03-02-BE | BE | Event hook: create a history entry when a signed-in library card reader opens or downloads an online book | S | 4 | Yes | No | 1 | 17 | 0
F-03 | FR-03-03 | Add history entries from borrowed physical books | Reader | WHEN a synced loan record of a library card account shows a borrowed book, the system SHALL add that book to the reading history of that reader. | UC:UC-07; DFD L0: Reader loan records (EIF) | FR-03-02 | Should | NC | FR-03-03-BE | BE | Job: create history entries from synced loan records (library card accounts only) | M | 8 | Yes | No | 1 | 18 | 0
F-03 | FR-03-04 | Mark reading status and progress | System | WHEN a signed-in reader sets a book to Reading or Finished and enters the progress, the system SHALL save the status and progress in the reading history. | UC:UC-07; DFD L0: Reading history & preferences (ILF) | FR-03-03 | Should | EI | FR-03-04-FE | FE | Screen: status selector and progress input | M | 8 | Yes | No | 1 | 19 | 4
F-03 | FR-03-04 | Mark reading status and progress | System | WHEN a signed-in reader sets a book to Reading or Finished and enters the progress, the system SHALL save the status and progress in the reading history. | UC:UC-07; DFD L0: Reading history & preferences (ILF) | FR-03-04 | Should | EI | FR-03-04-BE | BE | API: update status and progress of a history entry | S | 4 | Yes | No | 0 | 19 | 0
F-03 | FR-03-05 | Set reading preferences | System | WHEN a signed-in reader saves reading preferences, the system SHALL store them in the profile of that reader. | UC:UC-07 (preferences part); DFD L0: Reading history & preferences (ILF) | FR-03-04 | Could | EI | FR-03-05-FE | FE | Screen: reading preferences form | M | 8 | Yes | No | 1 | 20 | 4
F-03 | FR-03-05 | Set reading preferences | System | WHEN a signed-in reader saves reading preferences, the system SHALL store them in the profile of that reader. | UC:UC-07 (preferences part); DFD L0: Reading history & preferences (ILF) | FR-03-05 | Could | EI | FR-03-05-BE | BE | API: save reading preferences | S | 4 | Yes | No | 0 | 20 | 0
F-03 | FR-03-06 | Save a physical book to a personal list | System | WHEN a signed-in reader selects Save on a physical book, the system SHALL add the book to the saved books list of that reader. | UC:UC-12; DFD L0: Saved books list (ILF) | FR-03-05 | Should | EI | FR-03-06-FE | FE | Screen: Save button on the book detail page | S | 4 | Yes | No | 1 | 21 | 4
F-03 | FR-03-06 | Save a physical book to a personal list | System | WHEN a signed-in reader selects Save on a physical book, the system SHALL add the book to the saved books list of that reader. | UC:UC-12; DFD L0: Saved books list (ILF) | FR-03-06 | Should | EI | FR-03-06-BE | BE | API: add a book to the saved books list | S | 4 | Yes | No | 0 | 21 | 0
F-03 | FR-03-07 | View saved books with shelf locations | System | WHEN a signed-in reader opens the saved books list, the system SHALL display the saved books with the shelf location of each book. | UC:UC-12; DFD L0: Saved books list (ILF), Book placement & library layout (EIF) | FR-03-06 | Should | EQ | FR-03-07-FE | FE | Screen: saved books list with shelf locations | M | 8 | Yes | No | 1 | 22 | 4
F-03 | FR-03-07 | View saved books with shelf locations | System | WHEN a signed-in reader opens the saved books list, the system SHALL display the saved books with the shelf location of each book. | UC:UC-12; DFD L0: Saved books list (ILF), Book placement & library layout (EIF) | FR-03-07 | Should | EQ | FR-03-07-BE | BE | API: list saved books joined with placement data | S | 4 | Yes | No | 0 | 22 | 0
F-03 | FR-03-08 | Remove a saved book | System | WHEN a signed-in reader selects Remove on a saved book, the system SHALL delete the book from the saved books list of that reader. | UC:UC-12 (extension: remove from list, team decision); DFD L0: Saved books list (ILF) | FR-03-07 | Could | EI | FR-03-08-FE | FE | Screen: Remove action on the saved books list | S | 4 | Yes | No | 1 | 23 | 4
F-03 | FR-03-08 | Remove a saved book | System | WHEN a signed-in reader selects Remove on a saved book, the system SHALL delete the book from the saved books list of that reader. | UC:UC-12 (extension: remove from list, team decision); DFD L0: Saved books list (ILF) | FR-03-08 | Could | EI | FR-03-08-BE | BE | API: remove a book from the saved books list | S | 4 | Yes | No | 0 | 23 | 0
F-03 | FR-03-09 | Search books by chatting with the AI chatbot | System | WHEN a signed-in reader sends a message to the chatbot, the system SHALL reply with a list of catalogue books that match the request in the message. | UC:UC-08; DFD L0: Chatbot conversations (ILF) | FR-03-08 | Could | EO | FR-03-09-FE | FE | Screen: chat window with book result cards | M | 8 | No | No | 1 | 24 | 5
F-03 | FR-03-09 | Search books by chatting with the AI chatbot | System | WHEN a signed-in reader sends a message to the chatbot, the system SHALL reply with a list of catalogue books that match the request in the message. | UC:UC-08; DFD L0: Chatbot conversations (ILF) | FR-03-09 | Could | EO | FR-03-09-BE | BE | API: handle chat message, query the catalogue, build the reply | L | 16 | No | No | 0 | 24 | 0
F-03 | FR-03-09 | Search books by chatting with the AI chatbot | System | WHEN a signed-in reader sends a message to the chatbot, the system SHALL reply with a list of catalogue books that match the request in the message. | UC:UC-08; DFD L0: Chatbot conversations (ILF) | FR-03-09 | Could | EO | FR-03-09-INT | INT | Call the AI service inside the Library Core System with the reader message and context | M | 8 | No | Yes | 0 | 24 | 0
F-03 | FR-03-10 | Save chatbot conversations per reader | System | WHEN the chatbot exchanges a message with a signed-in reader, the system SHALL save the message in the conversation history of that reader. | UC:UC-08; DFD L0: Chatbot conversations (ILF) | FR-03-09 | Could | NC | FR-03-10-BE | BE | Persist chat messages per reader | S | 4 | Yes | No | 1 | 25 | 0
F-03 | FR-03-11 | Recommend books automatically | System | WHEN a signed-in reader opens the recommendations section, the system SHALL display a list of recommended books based on the reading history, preferences and chatbot conversations of that reader. | UC:UC-09 | FR-03-10 | Could | EO | FR-03-11-FE | FE | Screen: recommendation list | M | 8 | No | No | 1 | 26 | 5
F-03 | FR-03-11 | Recommend books automatically | System | WHEN a signed-in reader opens the recommendations section, the system SHALL display a list of recommended books based on the reading history, preferences and chatbot conversations of that reader. | UC:UC-09 | FR-03-11 | Could | EO | FR-03-11-BE | BE | Recommendation logic using history, preferences and chat data | L | 16 | No | No | 0 | 26 | 0
F-03 | FR-03-12 | Filter books by access format | System | WHEN a reader selects an access format filter, the system SHALL display only the books available in the selected format. | UC:UC-03; W0 Table 3 (filter is added by this platform; OPAC advanced filter has no format option) | FR-03-11 | Should | EQ | FR-03-12-FE | FE | Screen: access format filter on the advanced filter panel | S | 4 | Yes | No | 1 | 27 | 4
F-03 | FR-03-12 | Filter books by access format | System | WHEN a reader selects an access format filter, the system SHALL display only the books available in the selected format. | UC:UC-03; W0 Table 3 (filter is added by this platform; OPAC advanced filter has no format option) | FR-03-12 | Should | EQ | FR-03-12-BE | BE | API: query books by access format | S | 4 | Yes | No | 0 | 27 | 0
F-03 | FR-03-13 | Log anonymous online-book reads | System | WHEN any reader opens or downloads an online book from this platform, the system SHALL record the book and the time of the read without any reader identity. | UC:UC-03; team decision: anonymous read log kept to train the AI features; W0 Table 4 (Online book read log, ILF) | FR-03-12 | Could | NC | FR-03-13-BE | BE | Event hook: store the book ID and time of each online-book read, without reader identity | S | 4 | Yes | No | 1 | 28 | 0
F-03 | FR-03-14 | View access formats of a book | System | WHEN a reader opens a book detail page, the system SHALL list the access formats of the book (Physical, Online PDF). | UC:UC-03; DFD L0: Book catalogue (EIF) | FR-03-13 | Should | EQ | FR-03-14-FE | FE | Screen: access format list on the book detail page | S | 4 | Yes | No | 1 | 29 | 4
F-03 | FR-03-14 | View access formats of a book | System | WHEN a reader opens a book detail page, the system SHALL list the access formats of the book (Physical, Online PDF). | UC:UC-03; DFD L0: Book catalogue (EIF) | FR-03-14 | Should | EQ | FR-03-14-BE | BE | API: include access formats in book responses | S | 4 | Yes | No | 0 | 29 | 0
F-03 | FR-03-15 | Download the PDF of an online book | System | WHEN a signed-in reader selects Download PDF on an online book, the system SHALL deliver the PDF file of that book. | UC:UC-03; DFD L0: Book catalogue (PDF files, EIF) | FR-03-14 | Must | EQ | FR-03-15-FE | FE | Screen: Download PDF button with sign-in prompt | S | 4 | Yes | No | 1 | 30 | 4
F-03 | FR-03-15 | Download the PDF of an online book | System | WHEN a signed-in reader selects Download PDF on an online book, the system SHALL deliver the PDF file of that book. | UC:UC-03; DFD L0: Book catalogue (PDF files, EIF) | FR-03-15 | Must | EQ | FR-03-15-BE | BE | API: check reader session and stream the PDF file | M | 8 | Yes | No | 0 | 30 | 0
F-03 | FR-03-15 | Download the PDF of an online book | System | WHEN a signed-in reader selects Download PDF on an online book, the system SHALL deliver the PDF file of that book. | UC:UC-03; DFD L0: Book catalogue (PDF files, EIF) | FR-03-15 | Must | EQ | FR-03-15-INT | INT | Fetch the PDF file from the internal library system | M | 8 | Yes | Yes | 0 | 30 | 0
F-04 | FR-04-01 | Sign in with library card and email OTP | Reader | WHEN a reader submits a valid library card number and the correct OTP sent to the email declared on that card, the system SHALL start a signed-in session for that reader. IF the library card number is not found, or the OTP is incorrect or expired, THEN the system SHALL reject the sign-in and display an error message. | UC:UC-11; DFD L0: Reader accounts (EIF) | – | Must | EI | FR-04-01-FE | FE | Screen: card number and OTP entry, with error message | M | 8 | Yes | No | 1 | 31 | 4
F-04 | FR-04-01 | Sign in with library card and email OTP | Reader | WHEN a reader submits a valid library card number and the correct OTP sent to the email declared on that card, the system SHALL start a signed-in session for that reader. IF the library card number is not found, or the OTP is incorrect or expired, THEN the system SHALL reject the sign-in and display an error message. | UC:UC-11; DFD L0: Reader accounts (EIF) | FR-04-01 | Must | EI | FR-04-01-BE | BE | API: check card, request OTP, verify OTP, create session, reject with error when card not found or OTP wrong or expired | M | 8 | Yes | No | 0 | 31 | 0
F-04 | FR-04-01 | Sign in with library card and email OTP | Reader | WHEN a reader submits a valid library card number and the correct OTP sent to the email declared on that card, the system SHALL start a signed-in session for that reader. IF the library card number is not found, or the OTP is incorrect or expired, THEN the system SHALL reject the sign-in and display an error message. | UC:UC-11; DFD L0: Reader accounts (EIF) | FR-04-01 | Must | EI | FR-04-01-INT | INT | Look up the card number and declared email in the internal reader accounts | M | 8 | Yes | Yes | 0 | 31 | 0
F-04 | FR-04-02 | Register or sign in with email OTP | Reader | WHEN a visitor submits an email address and the correct OTP, the system SHALL create an online account if none exists for that email and start a signed-in session. | UC:UC-11; DFD L0: Online reader accounts (ILF) | FR-04-01 | Must | EI | FR-04-02-FE | FE | Screen: email and OTP entry | S | 4 | Yes | No | 1 | 32 | 4
F-04 | FR-04-02 | Register or sign in with email OTP | Reader | WHEN a visitor submits an email address and the correct OTP, the system SHALL create an online account if none exists for that email and start a signed-in session. | UC:UC-11; DFD L0: Online reader accounts (ILF) | FR-04-02 | Must | EI | FR-04-02-BE | BE | API: create account if new, verify OTP, create session | M | 8 | Yes | No | 0 | 32 | 0
F-04 | FR-04-03 | Sign in with Google | Reader | WHEN a visitor completes the Google sign-in, the system SHALL create an online account if none exists for that Google account and start a signed-in session. | UC:UC-11; DFD L0: Online reader accounts (ILF) | FR-04-02 | Could | EI | FR-04-03-FE | FE | Screen: Continue with Google button | S | 4 | Yes | No | 1 | 33 | 4
F-04 | FR-04-03 | Sign in with Google | Reader | WHEN a visitor completes the Google sign-in, the system SHALL create an online account if none exists for that Google account and start a signed-in session. | UC:UC-11; DFD L0: Online reader accounts (ILF) | FR-04-03 | Could | EI | FR-04-03-BE | BE | API: verify Google token, create account if new, create session | M | 8 | Yes | No | 0 | 33 | 0
F-04 | FR-04-03 | Sign in with Google | Reader | WHEN a visitor completes the Google sign-in, the system SHALL create an online account if none exists for that Google account and start a signed-in session. | UC:UC-11; DFD L0: Online reader accounts (ILF) | FR-04-03 | Could | EI | FR-04-03-INT | INT | Integrate Google sign-in (OAuth 2.0) | M | 8 | Yes | Yes | 0 | 33 | 0
F-04 | FR-04-04 | Send and verify email OTP | System | WHEN an OTP is requested for an email address, the system SHALL email a one-time code that expires after 5 minutes and can be used only once. | UC:UC-11 | FR-04-03 | Must | NC | FR-04-04-BE | BE | OTP generation, expiry, single use and attempt limit | M | 8 | Yes | Yes | 1 | 34 | 0
F-04 | FR-04-04 | Send and verify email OTP | System | WHEN an OTP is requested for an email address, the system SHALL email a one-time code that expires after 5 minutes and can be used only once. | UC:UC-11 | FR-04-04 | Must | NC | FR-04-04-INT | INT | Integrate an email delivery service | M | 8 | Yes | Yes | 0 | 34 | 0
F-04 | FR-04-05 | Link an online account to a library card | Reader | WHEN a signed-in online account reader submits a valid library card number and the correct OTP sent to the email declared on that card, the system SHALL attach the card number to the profile of that reader. | UC:UC-13; DFD L0: Online reader accounts (ILF), Reader accounts (EIF) | FR-04-04 | Could | EI | FR-04-05-FE | FE | Screen: link library card form with OTP entry | S | 4 | Yes | No | 1 | 35 | 4
F-04 | FR-04-05 | Link an online account to a library card | Reader | WHEN a signed-in online account reader submits a valid library card number and the correct OTP sent to the email declared on that card, the system SHALL attach the card number to the profile of that reader. | UC:UC-13; DFD L0: Online reader accounts (ILF), Reader accounts (EIF) | FR-04-05 | Could | EI | FR-04-05-BE | BE | API: verify card OTP and attach card number to the profile | M | 8 | Yes | No | 0 | 35 | 0
F-04 | FR-04-06 | Reject linking when both profiles hold data | Reader | IF the library card already belongs to a profile that holds data, THEN the system SHALL reject the link request and display a message that merging profiles is not supported. | UC:UC-13; W0 Table 3 (merging two reader profiles is out of scope) | FR-04-05 | Could | NC | FR-04-06-BE | BE | Check: reject the link when the card profile already holds data | S | 4 | Yes | No | 1 | 36 | 0
F-04 | FR-04-07 | Sign in On-site Staff with internal library account | Library Staff | WHEN On-site Staff submit valid internal library account credentials, the system SHALL start a staff session and open the staff page. | UC:UC-10; UC:UC-13; DFD L0: Staff accounts (EIF) | FR-04-06 | Must | EI | FR-04-07-FE | FE | Screen: staff sign-in and staff page menu | S | 4 | Yes | No | 1 | 37 | 4
F-04 | FR-04-07 | Sign in On-site Staff with internal library account | Library Staff | WHEN On-site Staff submit valid internal library account credentials, the system SHALL start a staff session and open the staff page. | UC:UC-10; UC:UC-13; DFD L0: Staff accounts (EIF) | FR-04-07 | Must | EI | FR-04-07-BE | BE | API: staff sign-in and staff session | M | 8 | Yes | No | 0 | 37 | 0
F-04 | FR-04-07 | Sign in On-site Staff with internal library account | Library Staff | WHEN On-site Staff submit valid internal library account credentials, the system SHALL start a staff session and open the staff page. | UC:UC-10; UC:UC-13; DFD L0: Staff accounts (EIF) | FR-04-07 | Must | EI | FR-04-07-INT | INT | Verify staff credentials against the internal library accounts | M | 8 | Yes | Yes | 0 | 37 | 0
F-04 | FR-04-08 | Enforce sign-in and staff access control | Library Staff | WHEN a request to a protected reader action or to the staff page has no valid session for the required role, the system SHALL deny the request. | W0 Table 1 (Login required: UC-04, UC-07, UC-08, UC-09, UC-12, UC-14; Staff login: UC-10, UC-13) | FR-04-07 | Must | NC | FR-04-08-BE | BE | Session validation and role check (RBAC) middleware on protected endpoints | M | 8 | Yes | Yes | 1 | 38 | 0
F-04 | FR-04-09 | Sync catalogue, shelf placement and library layout | System | WHEN the daily sync time is reached, the system SHALL import the catalogue, the shelf codes, and the floors and rooms from the internal library system without writing back to it. | DFD L0: Book catalogue (EIF), Book placement & library layout (EIF) | FR-04-08 | Must | NC | FR-04-09-INT | INT | Scheduled import of catalogue, shelf codes, floors and rooms from the internal system | L | 16 | Yes | Yes | 1 | 39 | 0
F-04 | FR-04-10 | Sync loan records | Reader | WHEN the daily sync time is reached, the system SHALL import the loan records of library card accounts from the internal library system without writing back to it. | DFD L0: Reader loan records (EIF) | FR-04-09 | Must | NC | FR-04-10-INT | INT | Scheduled import of loan records from the internal system | M | 8 | Yes | Yes | 1 | 40 | 0
F-04 | FR-04-11 | Handle sync failures | System | IF a sync run fails, THEN the system SHALL keep the last successful data, retry up to 3 times and write the error to the audit log. | Derived: FR-04-09 and FR-04-10 | FR-04-10 | Should | NC | FR-04-11-BE | BE | Retry policy and last-good-data fallback for sync jobs | M | 8 | Yes | Yes | 1 | 41 | 0
F-04 | FR-04-12 | Keep an audit log | System | WHEN a sign-in, a label print, a review removal or a sync run happens, the system SHALL write an audit entry with the actor, the action and the time. | Derived: F-04 scope (audit log) | FR-04-11 | Must | NC | FR-04-12-BE | BE | Audit logging service and storage | M | 8 | Yes | Yes | 1 | 42 | 0
F-04 | FR-04-13 | Deploy automatically | System | WHEN a change is merged to the main branch and the automated tests pass, the system SHALL build it and deploy it to the hosting environment. | Derived: F-04 scope (deployment) | FR-04-12 | Must | NC | FR-04-13-BE | BE | CI/CD pipeline and environments (staging, production) | L | 16 | Yes | Yes | 1 | 43 | 0
F-04 | FR-04-14 | Run automated tests on every change | System | WHEN a change is pushed to the repository, the system SHALL run the automated unit and integration tests and report the result. | Derived: F-04 scope (deployment); hidden technical work | FR-04-13 | Should | NC | FR-04-14-BE | BE | Automated test suite for core flows and pipeline test stage | L | 16 | Yes | Yes | 1 | 44 | 0
F-04 | FR-04-15 | Monitor errors and availability | System | WHEN the system raises an unhandled error or a health check fails, the system SHALL record the error with its context and notify the project team. | Derived: F-04 scope (operations); hidden technical work | FR-04-14 | Should | NC | FR-04-15-BE | BE | Error tracking, health check and alert to the project team | M | 8 | Yes | Yes | 1 | 45 | 0
Totals |  | L2 functions: 45 ¦ L3 work items: 78 | [10 empty] | 532 |  |  |  |  | 110
Integrity |  | All L3 rows have a numeric Base hours value

## W2_Rollup
W2 — Roll-up and threshold check
INPUT | W2_Costing, which reads W1 and W4. Nothing is typed here except the three shared observations at the bottom.
OUTPUT | Per-feature totals, the three headline figures for Session 8, and a pass/fail on every threshold — shown twice: as first written in W1, and after the W4 decisions.
PROCEDURE | 1. The integrator merges the branches and commits. 2. Recalculate. Fix nothing yet. 3. Just observe and assess whether the cost analysis is good enough
Per feature (using the effective priority, i.e. after W4)
Feature | Name | L2 | L3 | Base h (in use) | Must (p-h) | Should | Could | Won't | In-scope p-h | In-scope cost | Must % | Bottom-up h | Transactional FP | Bottom-up h per FP
F-01 | Book Location & Library Map | 5 | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 64 | 12 | 5.3333
F-02 | Reviews & QR | 10 | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 96 | 32 | 3
F-03 | Discovery, Reading History & Recommendation | 15 | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 176 | 46 | 3.8261
F-04 | Platform, Access & Operations | 15 | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 196 | 20 | 9.8
| PROJECT TOTAL | 45 | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 532 | 110 | 4.8364
Columns M-O compare the two sizing methods FEATURE BY FEATURE. Data functions (ILF / EIF) are counted once for the whole product, so column N holds transactional function points only — read column O as a RELATIVE figure. Features should cluster around a similar hours-per-FP ratio; the one sitting far from its siblings is where somebody mis-sized something, or where NC rows are carrying work that function points cannot see.
The three headline figures — always say which one you mean
Scenario | Scope | Person-hours | Cost (VND) | Meaning
Committed | Must only | #N/A | #N/A | What the team guarantees to deliver — the Minimum Usable SubseT
Expected | Must + Should | #N/A | #N/A | The figure given to the client; the base cash flow for Session 8
Ceiling | Must + Should + Could | #N/A | #N/A | If the Could contingency pool is never consumed
Threshold check — as first written (W1) vs after the W4 decisions
Indicator | As written | After W4 | Threshold | Verdict (after W4)
Must share of in-scope effort | 0% | #N/A | 60% | #N/A
Could share (contingency pool) | 0% | #N/A | 20% | #N/A
In-scope effort vs team capacity (p-h) | #N/A | #N/A | 360 | #N/A
Hidden technical work, share of effort | 0% | 0% | 10% | MISSING - revisit access control, deployment, tests
L3 rows above the hour ceiling | 0 | 0 | 0 | PASS
Feature count | 4 | 4 | 3-6 | PASS
Three observations the team carries into W4:

## W4_Prioritization
W4 — Repair and prioritise
INPUT | Initial priority from W1, the defect log from W3, and the team capacity from Parameters.
OUTPUT | An effective priority for every L2 function, each change carrying the rule it followed and a written justification. The effective priority flows back into W2_Costing and re-drives every total.
PROCEDURE | 1. Sort every W3 defect into one of three buckets: Fix now / Clarify / Reject. Rejecting is allowed, but the reason must be written down. 2. Repair STRUCTURE first: merge duplicates, add clock-triggered functions, add missing hidden work, split rows above the ceiling. 3. Recalculate and read the new numbers. 4. CUT: first move rows out to Won't-have, then demote Must -> Should -> Could. One sentence of justification per change. 5. Recalculate and confirm every threshold passes.
THE RULE ON THE BOARD | Cut by lowering priority, NEVER by lowering effort. Effort changes only when the technical scope of the row genuinely changes, and what was dropped must be written down.
Decision rules — every priority change must name the rule it followed
Rule | MoSCoW meaning | Test question |  | Kano category that usually maps here
R1 · Must | The release has no viable use without it | If it is absent on delivery day, is the release unusable? |  | Must-be — invisible when present, fatal when absent
R2 · Should | Important, but a workaround exists | Painful to leave out, yet the solution still works? |  | One-dimensional — more of it, more satisfaction
R3 · Could | Desirable, low impact if dropped | Would anyone notice within the first month? |  | Attractive — a delighter, never a Must
R4 · Won't | Agreed as out of scope for this release | Did the client accept deferring it, and is it in W0 Table 3? |  | Indifferent — asked for, but nobody actually cares
Feature | L2 ID | L2 function name | Initial priority | Rule applied | Kano category | New priority | Effective priority | Justification (required if changed) | Person-hours | Cost (VND)
F-01 | FR-01-01 | View book shelf location | Must |  |  |  | Must |  | #N/A | #N/A
F-01 | FR-01-02 | Browse the digital library map | Must |  |  |  | Must |  | #N/A | #N/A
F-01 | FR-01-03 | Show a book's room on the map | Should | R3 Could | Attractive | Could | Could | Workaround exists: readers still see floor, room and shelf code (FR-01-01) and can browse the map (FR-01-02); the deep link from a book to its highlighted room is a convenience. Nobody would miss it in the first month. | #N/A | #N/A
F-01 | FR-01-04 | Prepare the digital floor plan | Must |  |  |  | Must |  | #N/A | #N/A
F-01 | FR-01-05 | Check room codes against the internal system | Should |  |  |  | Should |  | #N/A | #N/A
F-02 | FR-02-01 | Write a book review | Must |  |  |  | Must |  | #N/A | #N/A
F-02 | FR-02-02 | View book reviews | Must |  |  |  | Must |  | #N/A | #N/A
F-02 | FR-02-03 | Edit own review | Could |  |  |  | Could |  | #N/A | #N/A
F-02 | FR-02-04 | Delete own review | Could |  |  |  | Could |  | #N/A | #N/A
F-02 | FR-02-05 | Open book information and reviews via QR code | Must |  |  |  | Must |  | #N/A | #N/A
F-02 | FR-02-06 | Count QR code scans | Should | R3 Could | Attractive | Could | Could | No reader-facing impact: scan counts only feed analysis and AI training, and the AI features are already Could. Dropping it does not block QR access (FR-02-05) or label printing (FR-02-08). | #N/A | #N/A
F-02 | FR-02-07 | Generate QR codes for new physical books | Must |  |  |  | Must |  | #N/A | #N/A
F-02 | FR-02-08 | Print QR code labels | Must |  |  |  | Must |  | #N/A | #N/A
F-02 | FR-02-09 | Report a review that breaks the rules | Could |  |  |  | Could |  | #N/A | #N/A
F-02 | FR-02-10 | Review and remove reported reviews | Could |  |  |  | Could |  | #N/A | #N/A
F-03 | FR-03-01 | View reading history | Should |  |  |  | Should |  | #N/A | #N/A
F-03 | FR-03-02 | Add a history entry when an online book is opened or downloaded | Should |  |  |  | Should |  | #N/A | #N/A
F-03 | FR-03-03 | Add history entries from borrowed physical books | Should |  |  |  | Should |  | #N/A | #N/A
F-03 | FR-03-04 | Mark reading status and progress | Should |  |  |  | Should |  | #N/A | #N/A
F-03 | FR-03-05 | Set reading preferences | Could |  |  |  | Could |  | #N/A | #N/A
F-03 | FR-03-06 | Save a physical book to a personal list | Should |  |  |  | Should |  | #N/A | #N/A
F-03 | FR-03-07 | View saved books with shelf locations | Should |  |  |  | Should |  | #N/A | #N/A
F-03 | FR-03-08 | Remove a saved book | Could |  |  |  | Could |  | #N/A | #N/A
F-03 | FR-03-09 | Search books by chatting with the AI chatbot | Could |  |  |  | Could |  | #N/A | #N/A
F-03 | FR-03-10 | Save chatbot conversations per reader | Could |  |  |  | Could |  | #N/A | #N/A
F-03 | FR-03-11 | Recommend books automatically | Could |  |  |  | Could |  | #N/A | #N/A
F-03 | FR-03-12 | Filter books by access format | Should |  |  |  | Should |  | #N/A | #N/A
F-03 | FR-03-13 | Log anonymous online-book reads | Could |  |  |  | Could |  | #N/A | #N/A
F-03 | FR-03-14 | View access formats of a book | Should | R4 Won't | Indifferent | Won't | Won't | Not rebuilt: for physical books the current OPAC already shows copies and shelf location, and for online books it already shows a download button. Readers still filter by format (FR-03-12). | #N/A | #N/A
F-03 | FR-03-15 | Download the PDF of an online book | Must | R4 Won't | Indifferent | Won't | Won't | Not rebuilt: the current OPAC already has the PDF download function for online books. No PDF delivery, session check or PDF fetch from the internal system is built on this platform. | #N/A | #N/A
F-04 | FR-04-01 | Sign in with library card and email OTP | Must |  |  |  | Must |  | #N/A | #N/A
F-04 | FR-04-02 | Register or sign in with email OTP | Must | R4 Won't | Indifferent | Won't | Won't | No online reader accounts in release 1: only library card holders sign in (FR-04-01), and online books need no account. | #N/A | #N/A
F-04 | FR-04-03 | Sign in with Google | Could | R4 Won't | Indifferent | Won't | Won't | Follows the removal of online accounts: Google sign-in only created online accounts. | #N/A | #N/A
F-04 | FR-04-04 | Send and verify email OTP | Must |  |  |  | Must |  | #N/A | #N/A
F-04 | FR-04-05 | Link an online account to a library card | Could | R4 Won't | Indifferent | Won't | Won't | Nothing to link once online accounts are removed. | #N/A | #N/A
F-04 | FR-04-06 | Reject linking when both profiles hold data | Could | R4 Won't | Indifferent | Won't | Won't | Only checked the link in FR-04-05, which is removed. | #N/A | #N/A
F-04 | FR-04-07 | Sign in On-site Staff with internal library account | Must |  |  |  | Must |  | #N/A | #N/A
F-04 | FR-04-08 | Enforce sign-in and staff access control | Must |  |  |  | Must |  | #N/A | #N/A
F-04 | FR-04-09 | Sync catalogue, shelf placement and library layout | Must |  |  |  | Must |  | #N/A | #N/A
F-04 | FR-04-10 | Sync loan records | Must |  |  |  | Must |  | #N/A | #N/A
F-04 | FR-04-11 | Handle sync failures | Should |  |  |  | Should |  | #N/A | #N/A
F-04 | FR-04-12 | Keep an audit log | Must |  |  |  | Must |  | #N/A | #N/A
F-04 | FR-04-13 | Deploy automatically | Must |  |  |  | Must |  | #N/A | #N/A
F-04 | FR-04-14 | Run automated tests on every change | Should |  |  |  | Should |  | #N/A | #N/A
F-04 | FR-04-15 | Monitor errors and availability | Should | R4 Won't | Indifferent | Won't | Won't | Deferred to fit team capacity: error tracking, health check and alerts are done by hand in release 1. Revisit if the client asks for uptime reporting. | #N/A | #N/A
Control panel — updates the moment column G changes
Indicator | Current | Threshold | Verdict
Must share of in-scope effort | #N/A | 60% | #N/A
Could share (contingency pool) | #N/A | 20% | #N/A
In-scope effort vs capacity (p-h) | #N/A | 360 | #N/A
Expected cost (Must + Should) | #N/A |  | The figure given to the client and used for NPV in Session 8

## W5_Handover
W5 — Baseline and handover
INPUT | The three headline figures from W2_Rollup and the assumption set from Parameters.
OUTPUT | Git tag fl-v1.0, business-case.md (three figures plus assumptions), tasks.md seeded risk-first, and one consolidated open-questions table.
PROCEDURE | 1. The commit message records that all thresholds pass. 2. Fill sections 1 and 2 below; export them as business-case.md. 3. In section 3, filter Effective priority = Must and sort Risk order ascending — that is the order for tasks.md. 4. Complete section 4 and confirm nothing is left dangling.
1. Three scenarios
Scenario | Person-hours | Cost (VND) | Role in the sensitivity analysis
Pessimistic — Must only | #N/A | #N/A | Lowest investment, lowest benefit
Base — Must + Should | #N/A | #N/A | The client figure; base cash flow for NPV
Optimistic — full scope | #N/A | #N/A | If the Could pool is never consumed
The three MoSCoW tiers ARE the three scenarios — no invented plus-or-minus 20%.
2. Assumptions
Assumption | Value | Source
Junior rate | 200000 | ITviec 2025-26 salary report
Senior rate | 300000 | ITviec 2025-26 salary report
Expert rate | 400000 | ITviec 2025-26 salary report
AI leverage — FE / BE / INT | 0.35 / 0.7 / 1 | Class parameter, recalibrated each cohort
Verification factor — precise / vague | 0.15 / 0.4 | Class parameter
Hours per function point | 3 | Class parameter — used only for the cross-check
Team capacity (person-hours) | 360 | 6 people x 12 weeks x 5 h
Money contingency on the Must set | 10% | Covers estimation error only. Do NOT add 20% on top of the Could pool — same buffer twice.
3. tasks.md seed — filter Effective priority = Must, sort Risk order ascending
L3 ID | Layer | Effective priority | Person-hours | Risk order
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
Risk order puts integrations first: the unknowns must be touched early, not at the end of DBIZ3.
4. Open questions still outstanding — paste back into the owning feature's spec.md
# | [NEEDS CLARIFICATION] question | Blocking? | Owning feature | Default applied
1 | [NEEDS CLARIFICATION: how does the platform learn that a reader opened or downloaded an online book - through a link from its book page, or only on the existing OPAC?] | Yes | F-03 | Assuming the book page links to the file through a tracked link, so FR-03-02 and FR-03-13 can record the event
2 | [NEEDS CLARIFICATION: does the internal library system hold a field that says whether a book is online, physical or both?] | Yes | F-03 | Assuming the synced catalogue carries an access format for every book, so FR-03-12 can filter on it
3 | [NEEDS CLARIFICATION: will the library tell the team when a room is added, renamed or removed, now that the room-code check (FR-01-05) is only a Should?] | No | F-01 | Assuming the team compares the room codes by hand before release
4 | [NEEDS CLARIFICATION: who watches errors and availability after release now that monitoring (FR-04-15) is Won't, and does the client need uptime reporting?] | No | F-04 | Assuming the team checks the system by hand in release 1
5 | [NEEDS CLARIFICATION: does the anonymous read log (FR-03-13) need a privacy notice or a retention period?] | No | F-03 | Assuming only the book ID and the time are stored, with no reader identity
6 | [NEEDS CLARIFICATION: does the 240 h team capacity cover Must + Should only, or also the Could pool?] | Yes | All | Assuming Must + Should must fit in 240 h; the Could pool is optional

## W6_CashFlow
W6 — Cash Flow
1. Assumptions
Assumption | Value | Unit
Discount rate (WACC / hurdle rate) | 12% | % per year
Evaluation horizon | 5 | years (1 to 5)
Annual running cost as % of build cost | 15% | % of build / year
Contingency rate on the Must set | 10% | % of Must cost
Must-set cost (contingency base) | #N/A | VND
Steady-state annual benefit by MoSCoW tier
Tier | x
Must | 30000000
Should | 15000000
Could | 10000000
Adoption ramp-up
Year | Unit | 0 | 1 | 2 | 3 | 4 | 5
Share of steady-state benefit realised | % of steady state | 0% | 40% | 70% | 100% | 100% | 100%
Scenario definition and Year-0 investment
Scenario (from W5) | Must in scope (1/0) | Should in scope (1/0) | Could in scope (1/0) | Build cost (W5) | Contingency | Year-0 investment | Steady-state benefit / year | Running cost / year
Pessimistic — Must only | 1 | 0 | 0 | #N/A | #N/A | #N/A | 30000000 | #N/A
Base — Must + Should | 1 | 1 | 0 | #N/A | #N/A | #N/A | 45000000 | #N/A
Optimistic — full scope | 1 | 1 | 1 | #N/A | #N/A | #N/A | 55000000 | #N/A
2. Cash flow per scenario (VND)
Pessimistic — Must only — Year-0 investment 51,942,000 VND
Line item | Unit | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Year inside horizon? (1 = yes) | flag | 1 | 1 | 1 | 1 | 1 | 1
Benefits | VND | 0 | 12000000 | 21000000 | 30000000 | 30000000 | 30000000
Running cost | VND | 0 | #N/A | #N/A | #N/A | #N/A | #N/A
Investment (build + contingency) | VND | #N/A | 0 | 0 | 0 | 0 | 0
Net cash flow | VND | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Cumulative net cash flow | VND | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Discount factor | 1/(1+r)^t | 1 | 0.89286 | 0.79719 | 0.71178 | 0.63552 | 0.56743
PV of net cash flow | VND | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Cumulative PV | VND | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Payback(year in which cumulative turns >= 0) | years |  |  |  |  | #N/A
Base — Must + Should — Year-0 investment 71,462,000 VND
Line item | Unit | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Year inside horizon? (1 = yes) | flag | 1 | 1 | 1 | 1 | 1 | 1
Benefits | VND | 0 | 18000000 | 31500000 | 45000000 | 45000000 | 45000000
Running cost | VND | 0 | #N/A | #N/A | #N/A | #N/A | #N/A
Investment (build + contingency) | VND | #N/A | 0 | 0 | 0 | 0 | 0
Net cash flow | VND | -71462000 | #N/A | #N/A | #N/A | #N/A | #N/A
Cumulative net cash flow | VND | -71462000 | #N/A | #N/A | #N/A | #N/A | #N/A
Discount factor | 1/(1+r)^t | 1 | 0.89286 | 0.79719 | 0.71178 | 0.63552 | 0.56743
PV of net cash flow | VND | -71462000 | #N/A | #N/A | #N/A | #N/A | #N/A
Cumulative PV | VND | -71462000 | #N/A | #N/A | #N/A | #N/A | #N/A
Payback (year in which cumulative turns >= 0) | years |  |  |  |  | #N/A
Optimistic — full scope — Year-0 investment 103,002,000 VND
Line item | Unit | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Year inside horizon? (1 = yes) | flag | 1 | 1 | 1 | 1 | 1 | 1
Benefits | VND | 0 | 22000000 | 38500000 | 55000000 | 55000000 | 55000000
Running cost | VND | 0 | #N/A | #N/A | #N/A | #N/A | #N/A
Investment (build + contingency) | VND | #N/A | 0 | 0 | 0 | 0 | 0
Net cash flow | VND | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Cumulative net cash flow | VND | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Discount factor | 1/(1+r)^t | 1 | 0.89286 | 0.79719 | 0.71178 | 0.63552 | 0.56743
PV of net cash flow | VND | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Cumulative PV | VND | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Payback (year in which cumulative turns >= 0) | years |  |  |  |  | #N/A
3. Results
Metric | Pessimistic — Must only | Base — Must + Should | Optimistic — full scope
Year-0 investment (VND) | #N/A | 71462000 | #N/A
Steady-state benefit per year (VND) | 30000000 | 45000000 | 55000000
Total benefits over horizon (VND) | 123000000 | 184500000 | 225500000
Total running cost over horizon (VND) | #N/A | #N/A | #N/A
Net cash flow over horizon, undiscounted (VND) | #N/A | #N/A | #N/A
NPV (VND) | #N/A | #N/A | #N/A
IRR (% per year) | n/a | n/a | n/a
Payback, simple (years) | > horizon | > horizon | > horizon
Profitability index (PV of inflows / investment) | #N/A | #N/A | #N/A
Decision signal | ACCEPT | ACCEPT | #N/A